## Sheet1
Item | Description | Estimative (h) | Status | Total hours spent
1 | Review project | 222 | In process | 2
1.1 | Review what is done, pendencies and structure better the planning | 2 | In process
1.2 | Get references to study | 20
1.3 | Structure Jupyter notebook | 200 |  | 2
2 | Extract data
2.1 | Colect datasets (excel file) | 0.5 |  | 0
2.2 | Import excel to python | 0.5 |  | 0
2.3 | Analysis data | 1 |  | 0.5
3 | Transform data
3.1 | Treat data
3.2 | Split 2 stations into separated datasets
3.3 | Treat unexistent data (for raining)
3.3.1 | Weighted data (anual and monthly)
3.3.2 | Fill unexistent data
4 | Load data
4.1 | Make database for new dataset
4.2 | Reunite 2 stations into one dataset
4.3 | Extract new data from db to analysis
5 | Statistical analysis
5.1 | Maximum precipitation anually
5.2 | Determine return tax
5.2.1 | Frequency by Kimbal's method | 2
5.2.2 | Graphical plot RT x Precipitation | 2
5.2.3 | Linear regression for RT | 2
5.2.4 | Return time estimative | 1
5.2.5 | Model validation
5.3 | IDF curve
5.3.1 | Adjust the factor
5.3.2 | Determine pluviometric height for each return time
5.3.3 | Plot IDF curve for 5 10 and 25 years
5.3.4 | Model validation
6 | Modeling